CITY OF SAUSALITO      SIX-MONTH STRATEGIC OBJECTIVES

November 21, 2008 – May 1, 2009

B THREE-YEAR GOAL:  Attain fiscal stability

| # WHEN | ## WHO | ### WHAT | STATUS |  |  | COMMENTS |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | DONE | ON TARGET | REVISED |  |
| 1. By January 31, 2009 | Interim Finance Director | Present to the City Council for action a report on the utilization of outside consultants for TOT services. |  |  |  |  |
| 2. By February 1, 2009 | Community Development Director (lead) , working with the City Engineer, Public Works Division Manager and Council Finance Committee (Mayor Amy Belser, Council Member Mike Kelley) | Compare and recommend adjustments to Sausalito’s Building, Planning, Engineering and Public Works fees and fines, taking into account other Marin communities and recovery costs, and present to the City Council for action. |  |  |  |  |
| 3. By April 1, 2009 | City Manager, working with the Council Finance Committee (Mayor Amy Belser, Council Member Mike Kelley) | Identify at least three tax revenue options to present to the City Council for their consideration. |  |  |  |  |
| 4. By May 1, 2009 | Police Captain | Develop and present to the City Council for action a comprehensive Parking Plan for all lots and metered areas. |  |  |  |  |
| 5. By May 1, 2009 | Technology Manager | Implement a Springbrook Financial System upgrade and server upgrade. |  |  |  |  |
| 6. By May 1, 2009 | Finance Director, working with the Council OMIT Committee (Council Members Jonathan Leone and Mike Kelley) | Increase occupancy to 95% of available space at the MLK properties and maintain the same level of revenue. |  |  |  |  |
| 7. By May 1, 2009 | Interim Finance Director | Assess the City’s banking relationships and identify cost savings and possible revenue for the City. |  |  |  |  |

B THREE-YEAR GOAL:  Increase effectiveness and efficiency of the organization

| # WHEN | ## WHO | ### WHAT | STATUS |  |  | COMMENTS |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | DONE | ON TARGET | REVISED |  |
| 1. Monthly | City Manager, working with the Senior Management Team | Define and articulate to staff, City Council and the public the “back to basics” concept and how to implement it. |  |  |  |  |
| 2. By January 15, 2009 | Community Development Director | Revise and begin implementation of a Code Enforcement Program. |  |  |  |  |
| 3. By February 1, 2009 | Assistant to the City Manager | Hold training on the Document Management System. |  |  |  |  |
| 4. By February 1, 2009 | City Attorney | Recommend to the City Council for action a consultant to perform a municipal code update. |  |  |  |  |
| 5. By February 1, 2009 | Assistant to the City Manager | Hire and train a new HR Technician. |  |  |  |  |
| 6. By February 1, 2009 | City Manager | Hire a Finance Director. |  |  |  |  |
| 7. By February 28, 2009 | Community Development Director | Fill the vacant Deputy Planning Director position. |  |  |  |  |
| 8. By March 1, 2009 | City Council (Councilmember Weiner-lead) | Appoint 5 public members to the Disaster Preparedness Committee. |  |  |  |  |
| 9. By March 1, 2009 | Parks and Recreation Director | Hire a Special Events Coordinator. |  |  |  |  |
| 10. By March 1, 2009 | Technology Manager, working with the Emergency Operations Manager | Identify the equipment needs, cost and sources of money and present to the City Council for action. |  |  |  |  |
| 11. By April 1, 2009 | Technology Manager | Determine the cost of rewiring City Hall to accommodate a VOIP phone system, identify source(s) of funding and report to the City Council for action. |  |  |  |  |
| 12. By April 1, 2009 | Emergency Preparedness Manager, in coordination with internal and external stakeholders | Identify Block Captains throughout the city to address disaster preparedness. |  |  |  |  |
| 13. By April 1, 2009 | Public Works Director | Implement at least 3 “green” solutions recommended in the Energy Audit. |  |  |  |  |
| 14. By April 1, 2009 | Police Chief (lead) and Public Works Division Manager, working with the new Finance Director | Review and recommend to the City Council for action tiering benefits for new hires. |  |  |  |  |
| 15. By May 1, 2009 | Fire Chief, working with a consultant | Present to the City Council for action options regarding fire services consolidation. |  |  |  |  |
| 16. By May 1, 2009 | City Council (Council Member Leone-lead) | Ensure that each Board and Commission has sufficient members to achieve a quorum. |  |  |  |  |

DTHREE-YEAR GOAL:  Improve the infrastructure, with emphasis on finishing the public safety building

| # WHEN | ## WHO | ### WHAT | STATUS |  |  | COMMENTS |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | DONE | ON TARGET | REVISED |  |
| 1. Monthly | Public Safety Facilities Manager and Public Works Director | Provide the City Council an update on the public safety facilities construction. |  |  |  |  |
| 2. By December 15, 2008 | Public Works Director | Implement flow monitoring in compliance per the EPA order. |  |  |  |  |
| 3. By January 15, 2009 | Public Works Director | Provide a Quarterly Spill Report to the EPA per EPA order. |  |  |  |  |
| 4. At the January 20, 2009 City Council meeting | City Engineer | Recommend to the City Council for action the awarding of contracts for the Non-Motorized Transportation Pilot Program projects. |  |  |  |  |
| 5. By February 1, 2009 | Library Director | Complete implementation of City Hall Improvements Phase I. |  |  |  |  |
| 6. By February 1, 2009 | Public Works Director | Report to the City Council on proposed dates for implementation of CIP projects in the 2008-2010 budget. |  |  |  |  |
| 7. By March 1, 2009 | Police Lieutenant and Fire Battalion Chief | Identify and present to the City Council’s Public Safety Facilities Committee required furnishings, fixtures and equipment for new public safety facility buildings and proposed sources of funding. |  |  |  |  |
| 8. By March 1, 2009 | Parks and Recreation Director | Report to the City Council a schedule of park improvements with dates for starting each project. |  |  |  |  |
| 9. By March 1, 2009 | Library Director, with input from the City Hall Improvement Committee | Review and recommend to the City Council for action improvements to City Hall in 2009-2010 to be in Phase II. |  |  |  |  |
| 10. By April 1, 2009 | City Engineer | Recommend to the City Council for action the awarding of a contract for the development of the work scope for the next phase of street rehabilitation. |  |  |  |  |
| 11. By April 1, 2009 | Fire Chief | Develop a Three-Year Vegetation Management and Development Plan and present to the City Council for action. |  |  |  |  |
| 12. By April 1, 2009 | Parks and Recreation Director | Recommend to the City Council for action park improvements for Harrison Park. |  |  |  |  |
| 13. By May 1, 2009 | Technology Manager | Assess recommendations from the ADA Transition Plan update and recommend actions to the City Council Outreach MLK Information Technology and Transportation Committee (OMIT). |  |  |  |  |
| 14. By May 1, 2009 | Parks and Recreation Director | Complete the 2002 Parks Bond Act projects. |  |  |  |  |